## c.no.6137
S/NO. | CONTRACT NO. | PROJECT TITLE | ZONE | STATE | NAME OF CONTRACTOR | MTB | BPP & FEC | NAME OF CONSULTANT | CONTRACT SUM | LENGTH OF ROAD (KM) | PROJECT LENGTH(KM) | DATE OF AWARD | DATE OF COMMENCEMENT | DATE OF COMPLETION | EXTENDED DATE OF COMPLETION | 2019 APPROPRIATION ACT | AMOUNT CERTIFIED TO DATE (N) | % PHYSICAL PROGRESS | AMOUNT PAID TO DATE (N) | OUTSTANDING CERTS FOR PAYMENT (APPROVED) | AMOUNT OF OUTSTANDING CERTS. (N) | ADVANCE GRANTED | ADVANCE RECOVERED | ADVANCE OUTSTANDING
12 | 6137 | DUALISATION OF OBAJANA JUNCTION TO BENIN PHASE 2: SECTION III( AUCHI TO EHOR)C/NO.6137 | SS | ED | Dantata & Sawoe Construction Company Limited | N/A | BPP/S.1/Vol.X/12/096 & EC 33(14)8 of 17th Sept, 2014 | Tandam Engineering services | 34866400154.56 | 25 | 25 | 2012-12-03 | 2012-12-24 | 2016-12-23 | 2020-11-04 | 1594160757 | 11655630573.4205 | 13.41% | 10242791038.19 | BAL 4A, 7, 10 & 11 | 1412839535.2305 | 4980914307.791 | 0 | 4980914307.791
[9 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF!
4.8955e+12